## Infra Project Review
Gloucester City IDP Project Tracker
Legend
Infrastructure located outside Gloucester City boundary; identifed as key to SA growth
| Project Name | Type of Infrastructure | Priority Level | Project Status | Date Completed | Delivery Body | Agreed / Est. Cost | Funding Secured? | Funding Body | Timescales for Delivery (LTP) | Source | Description | Relevant Links / Sources
Transport & Public Realm | Elmbridge transport scheme (roundabout improvements) | Road (County Highways) | N/A | Completed | 2017 | Gloucestershire County Highways | £9.07m | Y | Local Growth Fund | 2015-2021 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031). | https://www.gloucestershire.gov.uk/gloucestershire-county-council-news/news-september-2017/elmbridge-let-the-count-down-begin/ https://www.gfirstlep.com/downloads/2018/sep-2-update2018v3.pdf
| A430 Llanthony Rd and St. Ann Way improvement | Road (County Highways) | Short term | Planning | n/a | Gloucestershire County Highways | £7.45m | Y | Gfirst LEP | 2015-2021 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031). The scheme is partly funded by the Gloucestershire Growth Deal, where £2m of funding has been invested by GFirst LEP. GA condition of the money being awarded is that the Llanthony Road scheme has to be complete by 2021. | https://www.gloucestershire.gov.uk/gloucestershire-county-council-news/news-january-2019/improving-the-traffic-flow-on-llanthony-road/
| A40 Over roundabout improvement (phase 2) | Road (County Highways) | Short term | Construction | n/a | Gloucestershire County Highways | £2.35m | Y | Gfirst LEP / Longford Housing Development | 2015-2021 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031). Gfirst LEP / Longford Housing Development were funders for project. | https://www.gloucestershire.gov.uk/media/2771/faqs_a40_over-67245.pdf
| St. Barnabas Roundabout enhancement | Road (County Highways) | Short term |  | n/a | Gloucestershire County Highways | £1m | Y | GFirst LEP | 2015-2021 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031). GFirst LEP agreed the Gloucestershire Growth Deal with the Government on the 7th of July 2014.
| A417 Missing Link | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | £250-500m | Y | DfT | 2021-2031 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031). | https://highwaysengland.citizenspace.com/he/a417-missing-link/
| Highway improvement A38 outer ring road corridor | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031).
| Highway improvement London Road / Denmark Road junction | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031).
| Junction improvement A40 Longford roundabout | Road (County Highways) | N/A | Completed | 2018 | Gloucestershire County Highways | Unknown | Y | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 and Consultation with County Highways | Project within the Countywide revenue highway project delivery priorities (2015-2031). The improvements were sought through the GD3 funding process to facilitate strategic developments at Longford, Innsworth and Twigworth. Details of the scheme proposals can be sourced from Tewkesbury Borough Council as they were the scheme sponsor. | https://www.gloucestershire.gov.uk/highways/major-projects-list/a40-over-roundabout-improvement-scheme/
| Junction improvement A40 over roundabout (phase 3) | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031). Enhancement for outbound city traffic with alternative river crossing
| A40/A417 C&G roundabout improvements | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | A40/A417 C&G roundabout capacity improvements by provision of a ‘free left turn lane’ from the A40 Barnwood Link approach. | Scheme Ref. 45 in LTP
| Junction improvement A417 Zoons Court roundabout | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Project within the Countywide revenue highway project delivery priorities (2015-2031).
| Junction improvement Priory Road providing bus advantage | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Project within the Countywide revenue highway project delivery priorities (2015-2031).
| Highway Improvement M5 Junction 11 bridge cluster works | Road (SRN) | Short term | Feasibility | n/a | Highways England | Unknown |  | Highways England | 2015-2020 |  | Project within the Countywide revenue highway project delivery priorities (2015-2031).
| A40 corridor improvements between M5 Junction 11 and Highnam Court linked to proposed new development | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Project within the Countywide revenue highway project delivery priorities (2015-2031).
| A38 Wall roundabout capacity improvements | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Providing a 3-lane circulatory on the roundabout between Barnwood Road/ A38 Eastern Avenue approaches
| A38/ A4173 improvements | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Remove roundabout and signalising junction. (with removal of Reservoir Road approach arm)
| A38/ A430/ B4008 Cole Avenue Grade separation | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Grade separation to allow straight through movement of north/ south traffic on A38 Southern Connector/ A430 corridor
| A40/ A417 roundabout improvements | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Upgrade signals to MOVA or SCOOT operation to optimise signal timings
| A430/ A417 Castlemeads | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Upgrade signals to MOVA or SCOOT operation to optimise signal timings
| A38 Crosskeys roundabout | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Upgrade signals to MOVA or SCOOT operation to optimise signal timings
| London Road/ Great Western Road improvements | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown | N | Gloucestershire County Highways | 2021-2031 | Consultation with County Highways | Scale of proposed developments at sites SA05, SA09 and SA13 (From the list of ‘Gloucester City Proposed Residential Development Allocations’) will necessitate junction infrastructure mitigation at London Road/ Great Western Road, Westgate Gyratory and The Quay, and at St Oswalds Road/ Priory Road.
| Westgate Gyratory and The Quay improvements | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown | N | Gloucestershire County Highways | 2021-2032 | Consultation with County Highways | Scale of proposed developments at sites SA05, SA09 and SA13 (From the list of ‘Gloucester City Proposed Residential Development Allocations’) will necessitate junction infrastructure mitigation at London Road/ Great Western Road, Westgate Gyratory and The Quay, and at St Oswalds Road/ Priory Road.
| St Oswalds Road/ Priory Road improvements | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown | N | Gloucestershire County Highways | 2021-2033 | Consultation with County Highways | Scale of proposed developments at sites SA05, SA09 and SA13 (From the list of ‘Gloucester City Proposed Residential Development Allocations’) will necessitate junction infrastructure mitigation at London Road/ Great Western Road, Westgate Gyratory and The Quay, and at St Oswalds Road/ Priory Road.
| Signal improvements at Gloucester Station | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown | N | Gloucestershire County Highways | 2021-2034 | Consultation with County Highways | Access at Horton Road crossing and the effects of increased rail service provision. Significant impact exacerbated by 200 houses proposed on Network Rail land. Support provision of new footbridge here
| B4063 corridor improvements in Churchdown linked to proposed new development | Road (County Highways) | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | LTP Policy Doc 4 | Project within the Countywide revenue highway project delivery priorities (2015-2031).
| Gloucester railway station enhancement | Rail | Short term | Planning | n/a | Gloucester City Council | £3.75m LGF | Y | Local Growth Fund | 2015-2021 |  | Countywide capital rail project delivery priorities (2015 to 2031) LTP Policy Document 5. The funds are scheduled for allocation in 2020/21, bringing in a further c£7.5m of public/private sector leverage and accelerating the delivery of c550 homes and 5.3ha of Brownfield land. Identified in GFirst LEP Forward Look - https://www.gfirstlep.com/downloads/library/287-growth_deal_forward_look_rev16_dec_2018.pdf https://www.gfirstlep.com/downloads/2018/sep-2-update2018v3.pdf
| N2: Mainline platforms at Gloucester | Rail | Long term | Feasibility | n/a | Network Rail | £50-100m |  |  | 2019-2024 |  | Countywide capital rail project delivery priorities (2015 to 2031) LTP Policy Document 5
| N3: Capacity improvements between Gloucester and Cheltenham Spa | Rail | Long term | Feasibility | n/a | Network Rail | £50-100m |  |  | 2019-2024 |  | Countywide capital rail project delivery priorities (2015 to 2031) LTP Policy Document 5
| N4: Capacity at Standish Junction | Rail | Long term | Feasibility | n/a | Network Rail | £35-75m |  |  | 2019-2024 |  | Countywide capital rail project delivery priorities (2015 to 2031) LTP Policy Document 5
| N5: Capacity between Standish Junction and Haresfield | Rail | Long term | Feasibility | n/a | Network Rail | £20-50m |  |  | 2019-2024 |  | Countywide capital rail project delivery priorities (2015 to 2031) LTP Policy Document 5
| N6: Capacity between Charfield and Ashchurch / Eckington | Rail | Long term | Feasibility | n/a | Network Rail | £75-175m
| Gloucester Transport Hub, new bus station | Bus | N/A | Completed | 2018 | Gloucester City Council | £6.4m LGF / £4.1M GCC local authority funds | Y | Gfirst LEP | 2015-2021 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031) | https://www.gfirstlep.com/downloads/2018/sep-2-update2018v3.pdf
| Bus advantage improvements for Metz Way corridor including off carriageway cycle lane improvements | Bus | Short term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2015-2021 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| Bus corridor improvements Gloucester – Cheltenham via Churchdown | Bus | Short term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2015-2021 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| Elmbridge strategic scheme | Bus | Short term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2015-2021 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| Local park and ride facilities | Bus | Short term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2015-2021 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| Bus advantage at signals at Innsworth Land and Oxtalls Lane | Bus | Long term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2021-2031 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| Bus advantage improvements for Bruton Way | Bus | Long term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2021-2031 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| Bus stop and bus advantage improvements for Gloucester to Lydney / Coleford / Cinderford corridors | Bus | Long term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2021-2031 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| Bus stop and bus advantage improvements for Stroud – Gloucester corridor | Bus | Long term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2021-2031 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| A40 corridor bus priority scheme (SEP 2014) | Bus | Long term | Feasibility | n/a |  | Unknown |  |  |  | LTP Policy Document 1 | The A40 corridor bus priority scheme listed in the SEP was withdrawn following due diligence appraisal. Gfirst LEP https://www.gfirstlep.com/downloads/2018/sep-2-update2018v3.pdf
| Strategic park and ride expansion at Waterwells | Bus | Long term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2021-2031 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| Strategic park and ride scheme for West of Severn | Bus | Long term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2021-2031 | LTP Policy Document 1 | Identified within Countywide capital bus project delivery priorities (2015 to 2031)
| Outer ring road network linking Walls roundabout to Cole Avenue | Cycling | Short term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2015-2021 | LTP Policy Document 2 | Cycleway identified as one of top six priorities in Gloucestershire.
| Access improvements for the A40 corridor between Cheltenham and Gloucester | Cycling | Long term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2021-2031 | LTP Policy Document 2 | Countywide capital cycle project delivery priorities (2015 to 2031)
| Access improvements to Gloucester and Sharpness Canal towpath | Cycling | Long term | Planning | n/a | Gloucester City Council | Unknown |  |  | 2021-2031 | LTP Policy Document 2 | Countywide capital cycle project delivery priorities (2015 to 2031)
| Countywide cycle infrastructure improvements | Cycling | Long term | Feasibility | n/a | Gloucester City Council | Unknown |  |  | 2021-2031 | LTP Policy Document 2 | Countywide capital cycle project delivery priorities (2015 to 2031)
| Highway improvement Westgate Gyratory | Cycling, walking and public realm | Long term | Feasibility | n/a | Gloucestershire County Highways | Unknown |  | Gloucestershire County Highways | 2021-2031 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031).
| Southgate Street Townscape Heritage Initiative | Walking and public realm | Short term | Feasibility | n/a | Gloucestershire County Highways | £1.2m | Y | Heritage Lottery Fund / GCC | 2015-2021 | Strategic Economic Plan 2.0 (2018) | Project within the Countywide revenue highway project delivery priorities (2015-2031). | https://www.gloucester.gov.uk/planning-development/conservation-regeneration/townscape-heritage-initiative/
| Schemes 1 to 9 - Gloucester Railway Station to Derby Road | walking and public realm | Short term | Planning | n/a | Gloucestershire County Highways | 24200 | Y | Highways England | 2021-2031 | Central Severn Vale Cycling and Walking Infrastructure Plan 2019 | £3.8m of potential investment by Highways England to improve cycle connectivity on the Strategic Road Network between Cheltenham and Gloucester.
| Schemes A to C - Derby Road to Bruton Way | walking and public realm | Short term | Planning | n/a | Gloucestershire County Highways | £5,000-10,000 | Y | Highways England | 2021-2031 | Central Severn Vale Cycling and Walking Infrastructure Plan 2019 | £3.8m of potential investment by Highways England to improve cycle connectivity on the Strategic Road Network between Cheltenham and Gloucester.
| Schemes D to F - Gloucester Rail Station underpass diversion | walking and public realm | Short term | Planning | n/a | Gloucestershire County Highways | 44800 | Y | Highways England | 2021-2031 | Central Severn Vale Cycling and Walking Infrastructure Plan 2019 | £3.8m of potential investment by Highways England to improve cycle connectivity on the Strategic Road Network between Cheltenham and Gloucester.
| Schemes 10 to 16 – Great Western Road | walking and public realm | Short term | Planning | n/a | Gloucestershire County Highways | 10250 | Y | Highways England | 2021-2031 | Central Severn Vale Cycling and Walking Infrastructure Plan 2019 | £3.8m of potential investment by Highways England to improve cycle connectivity on the Strategic Road Network between Cheltenham and Gloucester.
Flood Risk Management | Park wetland storage, Armscroft Park, Kingsholm and Wotton | Flood Risk Management | N/A | Completed | 2014 | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Flood gates, 162/164 Bristol Road, Moreland | Flood Risk Management | N/A | Completed | 2014 | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Clearance and repair of drain, 145 Bristol Road, Quedgeley Severn Vale | Flood Risk Management | N/A | Completed | 2013 | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| De-silting channel, Blackditch, Milton Avenue, Westgate | Flood Risk Management | N/A | Completed | 2013 | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Watercourse Clearance. Removal of vegetation and debris to improve flow at Trevor Road | Flood Risk Management | N/A | Completed | 2017 | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Watercourse clearance in 3 stretches in Quedgeley. | Flood Risk Management | N/A | Completed | 2017 | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| High level outfall into River Severn, Rea Lane, Westgate | Flood Risk Management | N/A | Completed | 2015 | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Renaturalise channel, Abbeydale | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Barnwood park balancing pond improvement, Barnwood | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Property level protection for 15/20 properties, Barnwood | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Property level protection, Hucclecote | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Appleton Way lagoon and green lane, Brookfield Road and Millbridge/Porchester Road culvery alterations, Hucclecote | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Building of public open space to rear of properties, Kingsholm and Wotton | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Recreational park wetlands, Podsmead | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Highclere Road – property level protection and flood alert system, Quedgeley Severn Vale | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Retrofit SuDS, St Peter’s School , Tuffley | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Earth bund extension and trash screen replacement. Surface water diversion,Tuffley | Flood Risk Management | Moderate | Feasibility | n/a | Gloucestershire County Council | Unknown |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Construction of a cut-off channel at poplar close (Recreation Ground), Podsmead Ward | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 13455 |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Improvements to culvert inlet headwall at Poplar Close (Recreation Ground), Podsmead Ward | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 19562 |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Improvements to surface runoff at the athletics track, Podsmead Ward | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 100386 |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Improvements to drainage infrastructure at the recreation ground, Podsmead Ward | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 97200 |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18)
| Replace Millbridge Rd culvert and enlarge downstream channel, Hucclecote CP | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 247050 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Alter highway at Green Lane culvert to allow flood water to re-enter the watercourse. Hucclecote CP | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 12398 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Remove culverted section of Wooton Brook at Cousley Close, Hucclecote CP | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 29325 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Replace the Green Lane culvert with a larger culvert, Hucclecote CP | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 36936 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Install new trash screen to the open channel , Podsmead Ward | Flood Risk Management | Moderate - high | Feasibility | n/a | Gloucestershire County Council | 6831 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Improvements to surface water drainage system and storage pond | Flood Risk Management | Moderate - high | Feasibility | n/a | Gloucestershire County Council | 12903 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Improvements to overland flow path at Milton Avenue | Flood Risk Management | Moderate - high | Feasibility | n/a | Gloucestershire County Council | 15028 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Retro-fit SuDS at Langate House | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 15000 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Drainage improvements at Robinswood Hill | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 15000 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Reinstate ditch to rear of properties, Tuffley Ward | Flood Risk Management | Moderate - Low | Feasibility | n/a | Gloucestershire County Council | 20000 |  | Gloucestershire County Council |  | Identified within the Local Flood Risk Management Strategy, annual progress and implementation plan (2016-2017)
| Property level protection at 63 Jersey Road | Flood Risk Management | Moderate - Low | Feasibility | n/a | Gloucestershire County Council | 5000 |  | Gloucestershire County Council |  | Identified within the Local Flood Risk Management Strategy, annual progress and implementation plan (2016-2017)
| Increase upstream flood storage near Hathorn Road | Flood Risk Management | Low | Feasibility | n/a | Gloucestershire County Council | 562500 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Property level protection at 57/59 Churchdown Lane | Flood Risk Management | Moderate - low | Feasibility | n/a | Gloucestershire County Council | 10000 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Installation of earth bund, flood barriers and pump (Castlevilla) | Flood Risk Management | Low | Feasibility | n/a | Gloucestershire County Council | 15000 |  | Gloucestershire County Council |  | Identified within the Local Flood Risk Management Strategy, annual progress and implementation plan (2016-2017)
| Property level protection on Shelly Av, Tennyson Av and Shakespeare Av | Flood Risk Management | Moderate - low | Feasibility | n/a | Gloucestershire County Council | 736230 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Walled compound and improved base slab for sub station | Flood Risk Management | Low | Feasibility | n/a | Gloucestershire County Council | 11529 |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18) | Annual progress and implementation plan (2016-2017)
| Walled compound and improved base slab for sub station | Flood Risk Management | Low | Feasibility | n/a | Gloucestershire County Council | 18630 |  | Gloucestershire County Council |  | Local Flood Risk Management Strategy Annual progress and implementation plan (2017/18) | Annual progress and implementation plan (2016-2017)
| Alney Island Improvements, River Severn | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2021-2031 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Cypress Gardens CM Scheme | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2021-2031 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Gloucester Screens Rationalisation | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2015-2021 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Sud Brook/Twyver Project | Flood Risk Management | High | Construction | n/a | Environment Agency | Unknown |  | Environment Agency | 2015-2021 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Love Your River Gloucester | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2021-2031 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| SUDs retrofitting in Gloucester City Centre | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2021-2031 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Dimore Brook SUDs retrofitting | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown | TBC | Enovert fund (application to be made) | 2021-2031 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Natural Flood Management (NFM) | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2021-2031 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Daniels Brook | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2015-2021 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Deans Walk, Property Level Protection, Gloucester | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2015-2021 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Gloucester to Tewkesbury River Severn Property Level Protection | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2015-2021 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Podsmead Playing Fields, Sports Complex SuDS | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2015-2021 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| River Severn, Hempstead and Rea, Gloucester, Flood Alleviation Scheme | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2015-2021 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Tewkesbury Road, Longford Property Level Protection | Flood Risk Management | High | Feasibility | n/a | Environment Agency | Unknown |  | Environment Agency | 2015-2021 | FCERM Current investment programme. Funding sought from range of sources including developer contributions and CIL
| Brookfield Rd - Culvert replacement | Flood Risk Management | High | Feasibility | n/a | Gloucestershire County Council | 36936 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Reinstating ditch which runs to the rear of properties, Forest View Road, Tuffley ward | Flood Risk Management | Moderate - high | Feasibility | n/a | Gloucestershire County Council | 20000 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Install property level protection to at risk properties, Hucclecote Ward | Flood Risk Management | Moderate - high | Feasibility | n/a | Gloucestershire County Council | 1099032 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| The installation of individual property level protection measures, 63 Jersey Rd, Barton and Tredworth Ward | Flood Risk Management | Moderate - high | Feasibility | n/a | Gloucestershire County Council | 5000 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| The installation of an earth bund, flood barriers and pump, Castlevilla, Sandhurst Lane, Kingsholm and Wotton Ward | Flood Risk Management | Moderate - low | Feasibility | n/a | Gloucestershire County Council | 15000 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Green Lane - Property Level Protection, Hucclecote Ward | Flood Risk Management | Moderate - low | Feasibility | n/a | Gloucestershire County Council | 286143 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Retro fitting of SuDs measures (i.e. rainwater gardens, etc) to reduce flooding issues, Finlay Community School, Matson and Robinswood Rd | Flood Risk Management | Moderate - low | Feasibility | n/a | Gloucestershire County Council | 20000 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
| Brookfield Rd - property level protection | Flood Risk Management | Moderate - low | Feasibility | n/a | Gloucestershire County Council | 368115 |  | Gloucestershire County Council |  | Identified within the Prioritised Flood Alleviation Scheme List (GCC LFRMS) (2017-18).
Education | Primary school adjacent to Innsworth SA | Primary & secondary education | High | Planning | n/a | Gloucestershire County Council | Unknown | Schedule of S106 List | Developer | 2019/20 | Consultation with County Council Education | The application for the development of Innsworth Strategic Allocation (SA) proposed a new 2 form entry primary school to be provided within 3.5 years of commencement of housing with a target of 2019/2020 being set.
| Primary school adjacent to North Brockworth SA | Primary & secondary education | High | Planning | n/a | Gloucestershire County Council | Unknown |  |  |  | Consultation with County Council Education | For North Brockworth SA a new primary school with early year’s provision was identified to be provided onsite.
| Winnycroft SA Developer contributions for education - including Robinswood School | Primary & secondary education | High | Planning | n/a | Gloucestershire County Council | 1277660 | Schedule of S106 List | Developer |  | Consultation with County Council Education | The planning statement submitted for the Winnycroft SA application identified that contributions would provide for improvements to education. The current schedule of S106 lists the developer as contributing £1,277,660 to primary education, specifically at Robinswood School
| Churchdown School adjacent to Innsworth SA | Primary & secondary education | High | Planning | n/a | Gloucestershire County Council | Unknown |  | Developer |  | Consultation with County Council Education | Churchdown School and Chosen Hill School are both forecast to be beyond capacity by 2021/22 - proposed application for Innsworth does not provide for development of a new secondary school.
| Chosen Hill School adjacent to Innsworth SA | Primary & secondary education | High | Planning | n/a | Gloucestershire County Council | Unknown |  | Developer |  | Consultation with County Council Education | Churchdown School and Chosen Hill School are both forecast to be beyond capacity by 2021/22 - proposed application for Innsworth does not provide for development of a new secondary school.
| Brockworth Millbrook Academy - Secondary School | Primary & secondary education | High | Planning | n/a | Gloucestershire County Council | 2376000 | Schedule of S106 List | Developer |  | Consultation with County Council Education | North Brockworth SA financial contributions will be made for mainstream secondary school places and for 6th form places and improvements to Brockworth Millbrook Academy
| Brockworth Millbrook Academy - 6th form | Primary & secondary education | High | Planning | n/a | Gloucestershire County Council | 367200 | Schedule of S106 List | Developer |  | Consultation with County Council Education | North Brockworth SA financial contributions will be made for mainstream secondary school places and for 6th form places and improvements to Brockworth Millbrook Academy
| Winnycroft SA Developer contributions for education - including Gloucester Academy | Primary & secondary education | High | Planning | n/a | Gloucestershire County Council | 1123416 | Schedule of S106 List | Developer |  | Consultation with County Council Education
| Gloucestershire STEM centres: STEM teaching facility upgrades at 5 sites across Gloucs. | Primary & secondary education | High | In delivery | n/a | Gloucestershire County Council | £2.096m |  |  |  | Consultation with County Council Education / Gfirst LEP Forward Look
| Tuffley Primary School Expansion | Primary & secondary education | High | Construction |  | Gloucestershire County Council | Unknown | Yes | s106 |  | Consultation with County Council Education
| 60 more places at Calton Primary School in Linden | Primary & secondary education | High | Construction |  | Gloucestershire County Council | Unknown | Yes | planning obligations |  | Consultation with County Council Education
Communities and Culture | Blackfriars and Quayside Regeneration | Various | Long term | Feasibility | n/a | Gloucester City Council | £4.13m | Y | Local Growth Fund |  | Gfirst LEP | https://www.gfirstlep.com/projects/blackfriars-and-quayside-regeneration/ April 19 - Currently in investment/development phase.
Green Infrastructure, Sport & Recreation | Northern Sports Hub (Oxstalls Sports Park) | Green Infrastructure, Sport & Recreation | N/A | Completed | 2017 | University of Gloucestershire | £18m | Y | University of Gloucestershire |  | Consultation with Gloucester City Council / PPS
| Southern Sports Hub (Blackbridge Sports and Community Hub) | Green Infrastructure, Sport & Recreation | High | Planning | N/A | Gloucester City Council / Active Gloucestershire | Unknown | N | Gloucester City Council / Active Gloucestershire |  | Consultation with Gloucester City Council / PPS
| Severn Vale School AGP resurfacing | Green Infrastructure, Sport & Recreation | Low | Feasibility | N/A | Severn Vale School | Unknown | N | Severn Vale School |  | Consultation with Gloucester City Council / PPS
| St Peters Roman Catholic School AGP resurfacing | Green Infrastructure, Sport & Recreation | N/A | Completed | N/A | St. Peters RC School | Unknown | N | St. Peters RC School |  | Consultation with Gloucester City Council / PPS
| King’s School (Archdeacon Meadow) new AGP | Green Infrastructure, Sport & Recreation | N/A | Completed | 2018 | Kings School | Unknown | N | Kings School |  | Consultation with Gloucester City Council / PPS
| Waterwells Sports Centre new AGP | Green Infrastructure, Sport & Recreation | Low | Proposed |  | Gloucester City Council / Active Gloucestershire | Unknown | N | Gloucester City Council / Active Gloucestershire |  | Consultation with Gloucester City Council / PPS
| The Glebe youth-size AGP | Green Infrastructure, Sport & Recreation | Low | Proposed |  | Gloucester City Council / Active Gloucestershire | Unknown | N | Gloucester City Council / Active Gloucestershire |  | Consultation with Gloucester City Council / PPS
Healthcare | healthcare and community hub at South Churchdown Strategic Allocation | Healthcare | High | Feasibility |  | NHS/ developer |  |  | Cost to Service Provider | 2021-2025 | Consultation with Gloucestershire CCG
| A new GP surgery at Innsworth Strategic Allocation | Healthcare | High | Feasibility |  | NHS/ developer |  |  | Cost to Developer | 2021-2025 | Consultation with Gloucestershire CCG
| A new GP surgery at North Brockworth Strategic Allocation | Healthcare | High | Feasibility |  | NHS/ developer |  |  | Cost to Developer | 2021-2025 | Consultation with Gloucestershire CCG
| A consolidation of up to 5 GP practices into 1 or 2 new surgery sites in Cheltenham | Healthcare | Desirable | Feasibility |  | GCCG / Service Provider |  |  | Cost to Service Provider | 2026-2031 | Consultation with Gloucestershire CCG
| A new purpose-built GP surgery at Quayside, Blackfriars in Gloucester to include relocation of 2 existing practices | Healthcare | High | Feasibility |  | GCCG / Service Provider |  |  | Cost to Service Provider | 2026-2031 | Consultation with Gloucestershire CCG
Waste | Former Moreton Valence Airfield EfW plant | Waste | N/A | Completed | 2019 | [6 empty] | Site of a 190,000 tonnes-per-year capacity EFW plant
Note on N57: Ella Phillips: This Plan was not in IDP Draft
Note on N98: Ella Phillips: check APIP (2016-17) vs. PFASL (2017-18)

## Data Validation
Infrastructure Type | Priority | Project status | Timescale | HIGHWAYS Priority scheme | Completion
Road (SRN) | Short term |  | 2015-2021 | Yes | 2010
Road (County Highways) | Long term | Planning | 2021-2031 | No | 2011
Rail |  | Feasibility | 2019-2024 |  | 2012
Bus |  | Construction |  |  | 2013
Walking and public realm |  | Completed |  |  | 2014
Cycling |  |  |  |  | 2015
Flood Risk Management |  |  |  |  | 2016
Early year education |  |  |  |  | 2017
Primary & secondary education |  |  |  |  | 2018
Higher education |  |  |  |  | 2019
Housing |  |  |  |  | n/a